## JIRA Data
Type | Project | Sprint | EPIC | Story | Task | Quality | Budget Planned | Budget Consumed | Budget Remaining | Saving Planned | Saving Achived | Saving Pending | Date | Story Points | Priority | Assignee | Status | Dependencies
Story | Alpha | Sprint 1 | User Auth | Login with SSO | Frontend implementation | 0 | 3000 | 1800 | 1200 | 400 | 200 | 200 | 2026-01-10 | 3 | High | Alice | Done
Task | Alpha | Sprint 1 | User Auth | Login with SSO | Unit tests | 1 | 1200 | 900 | 300 | 150 | 90 | 60 | 2026-01-14 | 2 | High | Bob | Done
Story | Alpha | Sprint 2 | User Auth | Password reset flow | API endpoint | 0 | 2500 | 2500 | 0 | 300 | 300 | 0 | 2026-01-28 | 5 | Medium | Carol | Done
Task | Alpha | Sprint 2 | User Auth | Password reset flow | Email template design | 0 | 800 | 400 | 400 | 100 | 50 | 50 | 2026-02-04 | 1 | Low | Dave | In Progress
Story | Beta | Sprint 3 | Reporting | Management dashboard | Data model | 0 | 5000 | 3000 | 2000 | 600 | 300 | 300 | 2026-02-11 | 8 | High | Eve | In Progress
Task | Beta | Sprint 3 | Reporting | Management dashboard | Chart components | 2 | 2200 | 1100 | 1100 | 250 | 100 | 150 | 2026-02-18 | 3 | Medium | Frank | In Progress
Bug | Beta | Sprint 3 | Reporting | Management dashboard | Fix date filter | 3 | 600 | 0 | 600 | 0 | 0 | 0 | 2026-02-20 | 1 | High | Grace | To Do
Story | Beta | Sprint 4 | Integrations | Connect to third-party API | OAuth handshake | 0 | 4000 | 4000 | 0 | 500 | 500 | 0 | 2026-03-05 | 5 | High | Henry | Done
Task | Gamma | Sprint 4 | Integrations | Connect to third-party API | Rate-limit handling | 1 | 1500 | 750 | 750 | 200 | 80 | 120 | 2026-03-12 | 2 | Medium | Iris | In Progress
Story | Gamma | Sprint 5 | Performance | Reduce API response time | Query optimisation | 0 | 3500 | 500 | 3000 | 450 | 50 | 400 | 2026-03-19 | 5 | Medium | Jack | To Do

## Instructions
JIRA Dashboard Template — Instructions
Required columns (do NOT rename or remove these):
Type — Ticket type: Story, Task, Bug, Sub-task, Epic
Project — Project key or name (e.g. Alpha, Beta)
Sprint — Sprint name (e.g. Sprint 1)
EPIC — Epic name the ticket belongs to
Story — Parent story description
Task — Task description
Quality — Integer quality score (0 = no issues)
Budget Planned — Planned budget in your currency
Budget Consumed — Budget spent so far
Budget Remaining— Remaining budget (can be formula = Planned - Consumed)
Saving Planned — Planned savings
Saving Achived — Achieved savings (note: keep original spelling)
Saving Pending — Pending savings
Date — Date in YYYY-MM-DD format
Story Points — Effort estimate (integer)
Priority — High / Medium / Low / Critical
Assignee — Person responsible
Status — To Do / In Progress / Done / Blocked / In Review
Dependencies — Optional free-text dependency notes
Tips:
• Keep column order exactly as shown in the JIRA Data sheet.
• Dates must be parseable by pandas (YYYY-MM-DD recommended).
• The 'Cost' column is ignored if present — safe to include or omit.
• Remove these instruction rows before uploading.